## Sample (hidden)
SL No | Feature/Screen Name | Issue Name | Attachment | Priority | Status | Type | Existing System | Issue Type | Production | UAT | QA Status | Dev. Status | Remarks | Bug Fixed Date
1 |  | Direct image uploads are not working.
2 |  | Clicking on a ticket does not open it directly; users need to click on the three-dot menu to view details.
3 |  | When a ticket is opened, the comment section should appear directly below the ticket details, but currently, it requires an extra click to access.
4 | all-tickets | Default view must be in list format; currently, it is showing grid view.
5 |  | If i want to assign ticket to a team, it's mandatory to select employee and task, but it shouldn't be
6 |  | ticket id second portion is random, it should be sequential or will not present there
7
8 |  | need ticket link column in all tickets view and report
9 | Dashboard ¦ Date Filtering | Date Filtering isn't funtioning more than 2 Month | https://prnt.sc/IMGrESJcshdL
10 | Dashboard ¦ Dropdown Box | Dropdown box is emplty, we need editable search in the box | https://prnt.sc/Cl3UmSI9Qeyg
11 | Dashboard ¦ Ticket Searching | Ticket Searching by Name is not funtioning | https://prnt.sc/6eRpptekY7WD
12 | Dashboard ¦ Ticket Searching | Search box is not editable | https://prnt.sc/xPjy3V3k765o
13 | Dashboard ¦ Ticket Management | Ticket Creation Button needs to be in front page | https://prnt.sc/Y7OG4G5bifQp
14 | Ticket Management | Forward Backward Button is hidden in page no 1 | https://prnt.sc/Ry152n8YTHLc
15 | Dashboard ¦ Ticket Template | Ticket Template showing, actually it's ticket creatin button | https://prnt.sc/XqBlYFN_hnul
16 | Ticket Management | Need to add Severity Option | https://prnt.sc/j7sZqAxB2BRH
17 | Company Profile | Company name overlapping | https://prnt.sc/15Ysl-ncE4uQ
18 | Company Profile | Add new ticket button not working | https://prnt.sc/TfIXImyQUf-L
19 | Ticket Management ¦ My Tickets | Signing off while commenting at any ticket
20 | Ticket Management ¦ My Tickets | Status Change Buttion in the ticket management
21 | Dashboard ¦ Search bar | Ticket can not be searched by Ticket_ID
22 | Dashboard ¦ Search bar | Tickets can not be filtered by date | https://jam.dev/c/baf7a5be-54e6-4030-a17f-b4836455f57e
23 | Dashboard ¦ Search bar | Company and department have not been added in ticket searching | https://jam.dev/c/2de72e5d-0982-42b2-9c10-e751121966de
24 | Dashboard ¦ Search bar | No clickable Search icon is added anywhere | https://drive.google.com/file/d/1wplEOnmsqyp6ZlN8uwsvYUNjxrD2aamh/view?usp=drive_link
25 | Dashboard | All the tickets are not categorized | https://drive.google.com/file/d/1JeZp6wZQ6Rp481AFeHOyL_9I2GF5i-61/view?usp=drive_link
26 | Dashboard | Ticket performance can not be displayed by month | https://jam.dev/c/b9db4faf-8f45-4835-8f8e-c16d2cb083b4
27 | Dashboard | Top 5 ticket performers can not be found by month | https://jam.dev/c/8f1819a9-ee1c-4713-aea7-e6cbe7d2db4d
28 | Home page | Sheba pulse logo is not attached in home page | https://drive.google.com/file/d/1WlzJOkrBawDOAqgvkC1ywizsHXfzyfna/view?usp=drive_link
29 | Ticket Management | Can not create ticket | https://jam.dev/c/7b80b126-b052-4699-85ef-315c6c617313
30 | Communication ¦ Message | It's not showing a message is 'sent', 'seen' or 'sending failed' | https://drive.google.com/file/d/1hutbTcco1OQanjcdKQtih2-ODvNsfJkJ/view?usp=drive_link
31 | Communication ¦ E-mail | Draft mails can not be saved in "Draft" automatically | https://jam.dev/c/b05c2c84-0df9-4b5c-b682-323a7bd41a25
32 | My profile | Can not update profile settings | https://jam.dev/c/fcbed168-fcca-4a4d-a856-a4a5e4b6ba7b
33 | My profile | Can not change the mode from active to deactive | https://jam.dev/c/de225c7d-1ab8-44b2-a953-938c9d50172d
34 | My profile | Can not edit profile information | https://jam.dev/c/6cc3d1c8-3b05-46da-be65-ad7fc6c3bfd3
35 | My profile | Doesn't show profile picture in 'my profile' icon | https://drive.google.com/file/d/1K-5ealO2vPxMlyn9WIObeeEFGciqIoPv/view?usp=drive_link
36 | Role Management ¦ Designation | Can not update role management status | https://jam.dev/c/8f257b18-8934-4cf5-a765-46b0e5c79671
37 | Role Management ¦ Groups | Can not update role management status | https://jam.dev/c/8f257b18-8934-4cf5-a765-46b0e5c79671

## Web (hidden)
SL No | Feature Name | Issue Details | Type
1 | Sign Up | (self registration is not open)
2 |  | Terms & conditions, privacy policy (not set)
Doesn't send verification code to (random) email (forget pass)
Doesn't send verification code to (random) mobile (forget pass)
3 | Company Profile | Tin(TIN) Bin(BIN) should be in capital letter
4 |  | Showing dummy data into the company profile segment
5 |  | If company name is larger then name is overlaping
6 | Company Profile--> Employees | Add new employee, Import - not functional
7 |  | Import option not funcational
8 |  | Search option not funcational
9 |  | Department, Sub-Department Filter not funcational & not data showing on the filter list
10 |  | Active Inactive leveling not reflect properly & not funcational
11 |  | Why add edit ticket option into the (3dots) option
12 |  | Delete option not functional
13 |  | Add Per page view option
14 |  | Pagination not wroking
15 |  | Add Employee Status Column (Active/Inactive)
16 |  | Back option not redirect properly. It redirect to ticket tab but it should be back employees Tab
17 |  | Active Inactive option not working (Employee Details)
18 |  | Print option not working (Employee Details)
19 |  | Edit option not functional (Employee Details)
20 |  | Dummy data showing into the ticket performance & pending ticket segment (Employee Details)
21 |  | No data showing into the filter & filter not funcational (Employee Details)
22 |  | Change header color (Pending ticket segment)
23 |  | Employee ID column should be shown before Employee Name Column
24 |  | Label should be ID instead of id (Search Option)
Employees' pending tickets> (3 dots) is not functional
25 | Company Profile --> Tickets | Search option not funcational
26 |  | Filter option not functional & no data showing into the list
27 |  | Add New Ticket option not functional
28 |  | Active Inactive leveling not reflect properly & not funcational
29 |  | View Details option not funcational
30 |  | Edit ticket option not funcational
31 |  | Delete option not functional
32 |  | Add Per page view option
33 |  | Pagination not wroking
34 |  | Ticket ID column should be shown before Ticket Name Column & Label should be "Ticket Name" instead of Ticket name
35 |  | Label should be ID instead of id (Search Option)
36 | User Management | Column sequence should be Employee ID, Employee Name, Department, Sub-Department, Contact Email, Status, Action
37 |  | Add User Active/Inactive Option
38 |  | Filter not working
Add Search Option
39 |  | Department, Sub-Department create option not found
40 |  | Drag & drop option not functional
41 |  | Why allow others file format into the user photo segement. Image file format only allowed in this segment
42 |  | Label should be Upload Image instead of Upload File
43 |  | Company name should be default select
44 |  | How to manage line manager
45 |  | Capture minimum info while user onboarding
46 |  | How to manage Role
47 |  | Label should be Submit instead of Add User
48 |  | Showing an error message while try to add user
49 |  | After updating user info showing wrong success message. Should be update user info related message instead of new add related message
50 |  | After updating user info, user info should be auto updated. Now it updated only after page refresh
51 |  | Add Per page view option
Label should be 'Update User Info' instead of Update User
52 |  | Label should be 'Edit' instead edit employee
53 | Role Management | After clicking on designation or groups option, options list gets hidden
| Role Management --> Designation | Add new designation option is not functional
54 |  | Status change option not functional
55 |  | Edit Option not functional
56 |  | Add Search Option
57 |  | Add Filter option
58 | Role Management --> Groups | Role management create update not functional
59 |  | Search option not funcational
60 |  | Filter option not functional & no data showing into the list
61 |  | Status change option not functional
62 |  | Role base permission feature not showing into the list
63 |  | Action> edit cancel button is not functional
64
65 | Communication --> Message | After clicking new chat (+) button, Sub-department is empty when tries to create new chat
66 |  | Sub-department of employee is empty when tries to create new group
67 |  | Doesn't show specific message time in conversation
68 |  | Can not upload group photo
69 |  | Can not change group name
70 |  | Can not send multiple media files at a time
71 |  | Can not view multiple photo from media by clicking right ,left button
72 |  | Upper arrow sign needs to change to lower arrow sign when clicking to watch media files
73 |  | When rotating a photo from row-shape to column-shape, the photo automatically maximizes and can not minimize.
74 |  | After clicking on three dot in a conversation, three dot is showing again which is not needed, because cross button is there.
75 |  | Team or Group only one name should be there,
76 |  | Media file doesn't show when it's "one to one conversation" .
77 |  | Group chats needs to be listed in a separate section
78 |  | Chat list needs a different light color from the conversation color.
79 |  | Can not delete a specific message
80 |  | Can not delete conversation from the chat list
81 |  | Needs to refresh every time for the new messages
82 |  | Can not search a message by keyword from message body
83 |  | New chat (+)button> after searching and clicking on the username,sometimes the search box is still showing but successfully goes to the expected conversation in the background | https://jam.dev/c/35937bc9-aa23-43da-b186-4a21145d1598
84 |  | Conversation interface page gets moves from up to down, should stay stable | https://jam.dev/c/618d65a3-d4e2-4e14-baf0-bea0da74e9b1
85 |  | Doesn't show a message is 'sent', or 'seen' or 'sending failed'
86 |  | Needs to refresh again and again to get the latest messages.
87
88 | Communication -> Email | Back and delete button are not in the right place
89 |  | Doesn't show any notification after receiving a new mail
90 |  | Doesn't show the new mail in "Bold" font for easy understanding
91 |  | Draft mails don't get saved in draft folder "automatically"
92 |  | Can not send image in mail
93 |  | Can not send image in reply body
94 |  | Can not search mail by mail subject
95 |  | The downside arrow button attached with send button is not functional
96 |  | Sending mail to own mail account
97
98 | Dashboard | Ticket can not be searched by Ticket_ID
99 |  | Tickets can not be filtered by date
100 |  | Ticket can not be searched by name
101 |  | Company and department names have not been added in ticket searching
102 |  | No clickable Search icon is added anywhere
103 |  | All the tickets are not categorized (ticket count mismatched)
104 |  | Ticket performance can not be displayed by month
105 |  | Top 5 ticket performers can not be found by month
106
107
108
109
110 | Ticket Management-> All tickets | Default Set up should be in LIST format, not grid format. both format will be active
111 |  | No need to move to next page while previous page is not filled up with tickets
112 |  | Back button directly return to the ticket list, Can not return to the previous step of ticket creation,
113 |  | Ticket forward feature is missing
114 |  | Ticket forwarding should be clear and concise
115 |  | Turning on doesn't show clearly which activity is turning on (required field)
116 |  | File upload feature is not functional (required field)
117 |  | after refreshing from the 2nd and 3rd step of the ticket creation, page is directly going to 1st step
118 |  | Step 1 (no employee is found for the role human resource, but still showing the employee suggestion from different role)
119 |  | After adding an employee as checker, approver or executor doesn't show any notification
120 |  | Comment edit history should be seen, if edit history can't be seen then remove edit option.
121 |  | If i assign ticket to a team, it's mandatory to select employee and task, but it shouldn't be like this
122 |  | New or tag field is "description type" here, but it should be dropdown, and there will be business unit name
123 |  | Ticket link column should be seen in ticket view and report in all tickets
124 |  | After raising one ticket, 'raise' option is still open to select, but it shouldn't be
125 |  | After closing a ticket, it's showing canceled, but it should show "closed"
126 |  | Ticket comment , details options should be fixed but user need to drag and shift right <> left to watch all the options
all ticket download option is not added, (csv file download option needed)

## App (hidden)
SL No | Feature/Screen Name | Issue Name | Attachment | Priority | Status | Type | Existing System | Issue Type | Production | UAT | QA Status | Dev. Status | Remarks | Bug Fixed Date
| Home> Ticket performance | Top 5 ticket performers can not be filtered by month
Can not search ticket by name or ID
Without refreshing, it shows top 0 ticket performers instead of Top 5 ticket performers after openning the app
| Login > Forget password | Doesn't send verification code to the (random) email address
Doesn't send verification code to the (random) mobile number
Doesn't show email suggestion (perviously logged in)
| Communication> Message | Needs to refresh conversation list to view the latest messages
Can not upload group profile photo
Doesn't show member suggestion in "add new member" while searching
| Communication > Email | Sending mail to own mail account
| Ticket management | can not create ticket

## BUG-Redwan (hidden)
Bug ID | Issue Title | Issue type | Module | Sub-module | Issue evidence | Note to dev | Dev comment | Priority | Severity
BUG_ID 01 | Ticket can not be searched by Ticket_ID | Functional | Dashboard | _ | https://jam.dev/c/c36bc306-57d3-4081-9199-6ce98b7a276b | When the input (ticket id) is given, no output is showing |  | Medium | Medium
BUG_ID 02 | Tickets can not be filtered by date | Functional | Dashboard | _ | https://jam.dev/c/baf7a5be-54e6-4030-a17f-b4836455f57e | When the input (date) is given, no output is showing |  | Medium | Medium
BUG_ID 03 | Company and department names have not been added in ticket searching | Functional | Dashboard | _ | https://jam.dev/c/2de72e5d-0982-42b2-9c10-e751121966de | Specifc tickets should be found according to the company and department . But these features don't have any data. |  | Medium | Medium
BUG_ID 04 | No clickable Search icon is added anywhere | UI | Dashboard | _ | https://drive.google.com/file/d/1wplEOnmsqyp6ZlN8uwsvYUNjxrD2aamh/view?usp=drive_link | If the ticket searching process is not auto-generated after giving search input(id/date), then there must be a search icon to click to find the expected ticket |  | Medium | Medium
BUG_ID 05 | All the tickets are not categorized | UI | Dashboard | _ | https://drive.google.com/file/d/1JeZp6wZQ6Rp481AFeHOyL_9I2GF5i-61/view?usp=drive_link | If total ticket count: 70, completed ticket: 7, ticket waiting for approval:53> Then, {70-(53+7)} = 10 more tickets are in the ticket list which are catergorized in another catergory |  | Low | Low
BUG_ID 06 | It's not showing a message is 'sent', 'seen' or 'sending failed' | UI | Communication | Message | https://drive.google.com/file/d/1hutbTcco1OQanjcdKQtih2-ODvNsfJkJ/view?usp=drive_link | When a mail is sent to another mail, it can not be understood that the mail is sent or not. |  | Medium | Low
BUG_ID 07 | Draft mails can not be saved in "Draft" automatically | Functional | Communication | Email | https://jam.dev/c/b05c2c84-0df9-4b5c-b682-323a7bd41a25 | If a mail is not sent , it should be saved in the draft folder, but nothing is showing and the mail body is gone. |  | Low | Low
BUG_ID 08 | Can not update profile settings | Functional | My profile | _ | https://jam.dev/c/fcbed168-fcca-4a4d-a856-a4a5e4b6ba7b | Profile Settings button is disabled |  | Medium | Low
BUG_ID 09 | Can not change the mode from active to deactive | Functional | My profile | _ | https://jam.dev/c/de225c7d-1ab8-44b2-a953-938c9d50172d | User profile got 2 options, active and deactive. But deactive option is not active or disabled. |  | Medium | Medium
BUG_ID 10 | Can not update role management status | Functional | Role Management | Designation | https://jam.dev/c/8f257b18-8934-4cf5-a765-46b0e5c79671 | Employee designation have two status, The one which is already turned on can not be turned off and which is turned off can not be turned on. |  | Medium | Medium
BUG_ID 11 | Can not update role management status | Functional | Role Management | Groups | https://jam.dev/c/8f257b18-8934-4cf5-a765-46b0e5c79671 | employee designation and groups have two status, The one which is already turned on can not be turned off and which is turned off can not be turned on. |  | Medium | Medium
BUG_ID 12 | Can not edit profile information | Functional | My profile | _ | https://jam.dev/c/6cc3d1c8-3b05-46da-be65-ad7fc6c3bfd3 | Edit button is inactive or disabled or got no data. |  | Medium | Low
BUG_ID 13 | Doesn't show profile picture in 'my profile' icon | UI | My profile | _ | https://drive.google.com/file/d/1K-5ealO2vPxMlyn9WIObeeEFGciqIoPv/view?usp=drive_link | As the picture is activated in the employee/user information, the same picture should be seen in the profile icon for easy recognition. |  | Medium | Low
BUG_ID 14 | Can not create ticket | Functional | Ticket Management | All tickets | https://jam.dev/c/7b80b126-b052-4699-85ef-315c6c617313 | Ticket creation failed. Doesn’t show the exact reason why ticket can't be created. A "one line statement" needs to be attached for explaining the failure. |  | High | High
BUG_ID 15 | Ticket performance can not be displayed by month | Functional | Dashboard | _ | https://jam.dev/c/b9db4faf-8f45-4835-8f8e-c16d2cb083b4 | To see the montly ticket performance such as raised ticket, approved ticket ,solved ticket 'filtering by month' section needs to be activated. For this,month names should be added in the dropdown list. |  | Medium | Medium
BUG_ID 16 | Top 5 ticket performers can not be found by month | Functional | Dashboard | _ | https://jam.dev/c/8f1819a9-ee1c-4713-aea7-e6cbe7d2db4d | To see top 5 ticket performers per month 'filtering by month' section needs to be activated. For this,month names should be added in the dropdown list. |  | Medium | Medium
BUG_ID 17 | Sheba pulse logo is not attached in home page | UI | Home page | _ | https://drive.google.com/file/d/1WlzJOkrBawDOAqgvkC1ywizsHXfzyfna/view?usp=drive_link | "Ticketing"-the word is showing on the left top of the home page instead of website's name(Sheba pulse) or it's logo. |  | High | Medium
| why need second page when first page is not filled up | UI | Ticket Management

## New feedbacks (hidden)
| Module | Sub-module | Issue Title | Type | Attachment | Priority | Date | Status | SOC Review | User visiblity | Super admin visiblity
1 | Ticket Management |  | After adding an user as checker, approver or executor doesn't show any notification to that user | It's working |  | High |  |  | Done
| Ticket Management |  | Also notification must be clickable
2 | Ticket Management | Create Template | After selecting a different department , it still shows the employee(previously selected from another department) in the selected option (Workflow) | It's working |  | Medium |  |  | Done
4 | Ticket Management |  | Comment history is taking time to load (need to refresh all the time) | It's working |  | Medium |  | Done | Done
3 | Ticket Management |  | After editing a comment, It doesn't show "Edited". | It's working |  | Medium |  | Done | Done
5 | Ticket Management |  | In ticket log, "ticket name" column needs to be changed to "Template name" | It's working |  | High |  | Done | Done
6 | Ticket Management |  | Ticket forward button needs to click twice some times | It's working |  | Low |  |  | Done
7 | Profile | My profile | Doesn't show my profile (showing 404 error) | It's working |  | High |  |  | Done
8 | Ticket Management |  | All Templates or tickets download option is missing (should be able to download tickets filtering by month) | New Requirement |  |  |  | 2nd phase
9 | Ticket Management |  | Create new template option goes missing in super-admin account, but edit template option remains there | It's working |  | High |  |  | Done
10 | Ticket Management |  | In user dashboard,Add New CC' should be in the CC section, but it's appearing in the Activity Log | It's working |  | Medium |  | Done | Done
11 | Ticket Management |  | Admin can not create template, only super admin can create | It's working |  | Medium |  |  | Done
12 | Ticket Management |  | In ticket history , 'creator' needs to be changed to 'Sender'. | It's working |  | Low |  | Done | Done
13 | Ticket Management |  | Doesn't show notification if a ticket is raised in the user's department | It's working |  | Medium |  | Done
14 | Ticket Management |  | While closing the ticket text message is 'close the ticket', but it shows the template name | It's working |  | High |  |  | Done
15 | Ticket Management |  | After refreshing the page, Admin and Super-admin account turns into 'user' account. Ticket log goes missing. Also 'user' account turns into admin and super-admin account | It's working |  | High
16 | Communication | Mail | While sending mail to an unauthorized mail, doesn't show any error message | It's working |  | Medium |  |  | Done
17 | Ticket Management | Approval Hub | Checker can not view the ticket as a checker immediately after raising the ticket. It takes time | It's working |  | Medium |  |  | Done
18 | Ticket Management | Ticket ID | Ticket ID is generated randomly. No serial number is maintained | It's working |  | Medium |  | Ticket ID Generated Automatic
19 | Communication | Mail | Sometimes E-mail features are showing error | It's working | https://jam.dev/c/4fe3ef8c-5ccc-49b9-a298-73a04fe00b35 | High |  |  | Done
20 | Communication | Mail | Buttons in primary mails are not functional | It's working | https://jam.dev/c/550d4a36-3418-4b50-b9ae-75120b3695b5 | Low |  |  | Done
21 | Communication | Mail | Sender can not understand the reciever has applied the mail or not. Replied mails needs to be in BOLD letter in the list and the last mail should show in that row, it is showing the first mail. | It's working |  | high |  |  | Done
22 | Communication | Mail | One account is crossing over another account. Sending mail to specific person is failing anonymously. Each account turns into one account which is the super-admin account "anamul.ah33@gmail.com". 'inbox' and 'sent' mails shows the mails of that one account. User and admin account turns into super-admin account for "ticket management" as well (specially after refreshing the page) | It's working | https://jam.dev/c/07a70394-ea82-4b46-ae5d-18b90730445e | High |  |  | Done
23 | Communication | Message | Unable to view conversation and unable to send messages. | It's working | https://jam.dev/c/c4b05c90-d817-46e5-a35e-918649611957 | High |  |  | Done
24 | Ticket management | Create template | Create new template option is showing in user account | It's working | https://drive.google.com/file/d/1JScdvUuQfkmE6ccvBxRtNZ4INzKNiRWA/view?usp=drive_link |  |  |  | Done
25 | Ticket management | Create Template | "Create template" option should always be on the super admin account , it goes missing | It's working |  |  |  |  | Done
26 | Ticket management |  | Add a column 'ticket headline' in ticket log Where all the tickets name will be visible behind the template name | Improvement
27 | Ticket management |  | In ticket history, details are not clear, | Improvement |  |  |  | 2nd phase
28 | Ticket management |  | After closing a ticket , the status should be saved as 'closed' , not 'completed' | It's working |  |  |  | Done | Done
29 | Ticket management |  | While raising a ticket to an user/admin, they should be able to forword or resolve that ticket, now they can only view that ticket as CC. They are automatically added in CC without adding them as CC. | New Requirement |  |  |  | 2nd phase
30 | Ticket management |  | 2nd 'question title' headline needs to be replaced by 'add attachment' in required fields for file upload | It's working |  |  |  |  | Ongoing
31 | Ticket management |  | After forwarding a ticket to a specific department, users of that department needs to get notification | It's working |  |  |  | Done | Done
32 | Ticket management |  | Ticket ID and template names needs to be corrected accordingly in different features | It's working |  |  |  | Done | Done
33 | Communication | Mail | Email forwarding option is not available | New Requirement |  |  |  | 2nd phase
34 | Ticket management |  | When checker or approver confirm checking or approving with a message "checking done..." where this message is stored? | It's working |  |  |  | Done | Done
35 | Ticket management | Approval Hub | For the approver, "Reject" button location needs to be changed from left bottom to right bottom just behind the 'Approve" button | It's working |  |  |  |  | Done
36 | Ticket management | Approval Hub | SLA Status and Ticket Working Status should be segregated and modified | Improvement | https://prnt.sc/TS5t-HdjxAVY |  |  | 2nd phase
37 | Ticket management |  | When checker or approver confirm checking or approving with a message "checking/approving done... ", where to find this message? | It's working |  |  |  | Done | Done
| Ticket management |  | It's not still implemented according to figma design | It's working | https://prnt.sc/IVaBamkCvHsx
| Dashboard |  | It's not covered all according to Figma Design | 2nd Phase | https://prnt.sc/gJauVSWO5nTk
| Raise Ticket | CC | Need to enable Multiple Department Selection | It's working | https://prnt.sc/YHYmX9zgfwna |  | 21.07.25
|  |  | Both Priority and Severity search option need to add in the top bar,only 'ticket log' and 'my tickets' has severity column,but no filtering | It's working | https://prnt.sc/hTcTYLJUWWY2 |  | 21.07.25
|  | Ticket log | Date Filter Need to be added in the Ticket Logs Portal | It's working | https://prnt.sc/ZizBWdAqSlTw
|  | Create template | Add sub-department option in template creation, need to show sub-department column | It's working |  |  | 21.07.25
|  |  | Super admin needs to see all tickets count in dashboard, not just his own raised tickets. | It's working

## 20-21 Sept
Bug ID | Module | Sub-module | Issue Title | Type | Priority | Attachment | Status | SOC Review | UBD Review
B_ID_1 | Communication | Message | After sending a message, it doesn't send immediately. It requires clicking on another chat to make this visible. Again, messages are showing after sending two messages. In group conversation, it's working fine. | Bug | Critical |  |  |  | Passed
B_ID_2 | Ticket Management | All tickets | Despite removing the department, sub-department; it is still showing department column in all tickets | Bug | High | https://prnt.sc/3wOCenUaaV2x |  |  | Need decisions from pulse team regarding a solution we provided
B_ID_3 | Ticket Management | Ticket Details | severity and priority is not in the correct serial. Severity and Priority needs to be together one after one. Again, for priority, short form P1,P2... is missing | Improvement | High | https://prnt.sc/GCZsm_8Fgh5q |  |  | Passed
B_ID_4 | Ticket Management | Activity Log | In workflow based ticket, log is "ticket will approve by assignee" , but it is showing "ticket will approve from assignee" | Bug | High | https://prnt.sc/v2K0hNHzb7tG |  |  | Passed
B_ID_5 | Ticket Management | All tickets Assign to me | After closing the ticket, in 'all tickets' it is still showing resolve and forward button for assignee and others from assignee's dept, but in assign to me, it gets removed after resolving. After closing a ticket, there will be only Re-open option. | Bug | Critical | https://prnt.sc/f0ZPQ5y2U1Qn https://prnt.sc/uX3T9DlmrhT7 https://prnt.sc/38Lwf5u-wVIe |  |  | Passed
B_ID_6 | Ticket Management | Ticket status | Ticket status need to show under ticket title as like as "canceled" status. | Improvement | Critical | https://prnt.sc/VjRsD2-aH320 |  |  | Passed

## Feedback from 1st Phase
Item ID | Module | Sub-module | Issue Title | Type | Priority | Attachment
I_ID_1 | Ticket management | Ticket forwarding | After resolving a ticket by someone from the assignee's department, status gets resolved, but it still requires "resolve" by the assignee. Need to change the status for assignee as well. It should not require an assignee's action. After forwarding a ticket by the assignee's department it doesn't directly move to the person to whom the ticket has been forwarded. After forwarding by assignee only, the ticket gets forwarded. After resolving by anyone, ticket status should be resolved for everyone and need to show the log. | Bug | Critical
I_ID_2 | Ticket management | Ticket forwarding | After forwarding ticket to any user by assignee or assignee's department, the ticket should be visible and actionable to all the user's from that user's department (L2 forwarding) | Improvement | Critical
I_ID_3 | Ticket management | Ticket Status | After ticket forwarding, status is still showing "opened", it should show in-progress. After commenting on a ticket, status gets changed to in-progress which is fine. | Bug | High
I_ID_4 | Ticket management | User Search | While forwarding ticket, only 10 person is showing in user's search list | Bug | Critical
I_ID_5 | Ticket management | change priority | Assignee must not have the priority shifting option in three dot | Bug | Critical
B_ID_6
I_ID_6 | Communication | Mail Communication | email should also be searched from replied mail | Bug | Critical
I_ID_7 | Communication | Message | Text box is showing in one line while typing multiple lines for a single message. It should show in multiple lines according to text box size increasing. Also line breaks are not visible. | Improvement | Critical
I_ID_8 | Search | All search | Alphabetical shortcode search not working for feature and product | 1st phase due | Critical
I_ID_9 | User Management |  | NEED single user - multiple company assigning option | Requirement | High

## 2nd Phase
Sl | Module | Sub-module | Issue Title | Type | Priority | Attachment | Date | Status | SOC Review
P-2.1 | Ticket Management | Create Ticket | Both single user and Department assigning and forwarding by ticket creator, should be enabled in SLA based ticket , First checker(L1) should not be fixed from the template. Ticket will be forwarded from department(all users) to another department(all users) | Improvement | Critical
P-2.2 | Ticket Management | Create ticket | In SLA based tickets: in my role column- L1, L2, L3. also in ticket details, my role is showing checker. | Bug | High
P-2.3 | Ticket management | Sub-feature | Under All features, there needs to be a sub-category or sub-feature where sub-categories will be added against feature
P-2.4 | Ticket management | Activity log | After resolving the ticket by someone from assignee's department, it doesn't show in activity log "resolved by.........." it still shows "will check by assignee" and sla still continues for assignee if he doesn't resolve it from his account again. After forwarding a ticket by someone from assignee's department, ticket doesn't directly go to the forwarded person, it requires the first assignee to resolve it. | Bug | Critical
P-2.5 | Ticket management | Create ticket | While creating ticket, selected option from dropdown or checkbox goes missing | Improvement | High
P-2.6 | Ticket management | Status | SLA status and Working status needs to be in different column in all tickets | Requirement | High
P-2.7 | Ticket management | Required field | While selecting an option from dropdown during creating ticket, it requires two time selection (shouldn't require double click) | Improvement | High
P-2.8 | Ticket management | Ticket assign | Add a feature 'assign to my department' OR add a dropdown field for 'assign to me' and 'assign to my department' in all tickets | Improvement | High
P-2.9 | Ticket management | create ticket | User should be able to assign himself while creating ticket (SLA based), should be able to resolve and close the ticket | Improvement | High
P-2.10 | Ticket management | Create ticket | While creating ticket, category and sub-category will be searchable | Requirement | High
P-2.11 | Ticket management | Required field | Mandatory field from template should have star * mark (red) | Improvement | High
P-2.12 | Ticket management | CC | CC option should be availabe for second layer , L-2 department | Requirement | High
P-2.13 | Ticket management | CC | In workflow based ticket, while adding cc, 'forward' button should replace to 'add cc', | Improvement | Medium
P-2.14 | Ticket management | Create ticket | Need error message while creating ticket if any field(title/ description) is missing, not just in the required field part of the ticket | Improvement | Critical
P-2.15 | Ticket management | Comment | Ticket details UI - Comment section should be visible first after entering to ticket. 1st priority | Improvement | High
P-2.16 | Ticket management | Status | Ticket status should be in up side-left of the page after entering into the ticket. just like 'canceled' | Improvement | Critical
P-2.17 | Ticket management | Assigned ticket | Assignee/Assignee's department> my department> CC - priority level for an user | Improvement | Critical
P-2.18 | Ticket management | Ticket forwarding | after forwarding a ticket by someone from the assignee's department, the status for all the user of the same department should be "forwarded" | Improvement | High
P-2.19 | Ticket management | Ticket forward | SLA time should not be defined while forwarding ticket
P-2.20 | Ticket management | Ticket action | Enable ‘resolve, close, cancel, forward, re-open’ option for all the tickets which user can access. (Tickets created by user’s department or assigned to user’s department or forwarded to user’s department). | Improvement | Critical
P-2.21 | Ticket management | Status and report | After resolving a ticket by anyone, ticket status should be resolved for everyone. In the report resolved by user and department will be different column
P-2.22 | Ticket management | History | Ticket history needs to be more transparent for better understanding,After taking action by any one in the ticket all the logs(comment,forward,resolve, close) with date,time should be visible |  |  | https://prnt.sc/z5Gv7v_GbMI4
P-2.23 | Ticket management | Ticket creation | Ticket description editing should be disabled
P-2.24 | Ticket management | Ticket creation | The description box size needs to be enlarged automatically according to text size, shouldn't require manual size increasing
P-2.25 | Ticket management | Search
P-2.26 | Ticket management | Comment | Comments should be in the first part of ticket details box
P-2.27 | Ticket management | Activity log | While checking, approving, executing, rejecting, closing- need mandatory text field. the text should show in the activity log
P-2.28 | Ticket management | Activity log | In activity log. ticket closed by, canceled by, reopened by all the logs should be visible
P-2.29 | Ticket management | Create ticket | Create ticket button needs to add in every page (dashboard, communication , ticket management)
P-2.30 | Ticket management | SLA time | ticket forwarding will not change the resolve due time. SLA time will be fixed after creating ticket
P-2.31 | Ticket management | SLA time | In workflow based ticket, SLA time?? Action time??
P-2.32 | Ticket management | Assigned ticket | When a user is assignee in a ticket, in all tickets, his involvement type should be 'assignee' not "assignee's department" | Improvement | High
P-2.33 | Ticket management | ticket history | Ticket history is not transparent, Sender, Reciever. | Improvement | Medium
P-2.34 | Ticket management | Description | The description box edit option should be disabled after ticket creation
P-2.35 | Ticket management | Ticket details | Currently assigned will show "users name" if a single user gets assigned to a ticket. Currently assigned will show "department name" if a department gets assigned to a ticket.
P-2.36 | Ticket management | Status | Ticket Management: status filter needed; also show in Dashboard pie chart.
P-2.37 | Ticket management | All tickets | Unique and repeated tickets should be searchable and count visible.
P-2.38 | Ticket management | Department/ current department | Department column should show currently assigned department, in workflow based ticket, it will show current checker/approver/executor's department. After resolving,rejecting and executing, it needs to show ticket creator's department.
P-2.39 | Ticket management | Status | Severity and priority position should be replaced, In all tickets column, in ticket details, everywhere severity will come first, then priority.
| Ticket management | action access | Enable ‘resolve, close, cancel, forward, re-open’ option for all the tickets which user can access. (Tickets created by user’s department or assigned to user’s department or forwarded to user’s department).
P-2.40 | Communication | Email | Email Forwarding | Requirement | High
P-2.41 | Communication | Message | Message box will get increased according to text size, if the text get larger, message box will get larger and should not visible just in one line. After sending a message, line gaps should be visible in proper format. |  |  | https://prnt.sc/xchfnOqUNi26
P-2.42 | Communication | Message | Blank message should not be sent |  |  | https://prnt.sc/xchfnOqUNi26
P-2.43 | Communication | Message | Date should show for all the messages on a specific day
P-2.44 | Communication | Message | If messages are seen, it should show seen after clicking on the message and show how many people has seen
P-2.45 | Communication | Message | Need message forwarding option in three dot of the message
P-2.46 | Communication | Mail | need "All Mails" feature where all the mails will be stored and should be able to search mail by any text from 'sent', 'inbox', 'drafts' | Improvement | High
P-2.48 | Dashboard | Dashboard | In dashboard, after clicking on the status, it will redirect to those ticket list
P-2.49 | Dashbaord | Dashboard | Dashboard should display Top 5 issues in a pie chart.
P-2.50 | Dashboard | Dashboard | “Resolved by team and Closed by Team” need to be filtered in Dashboard.
P-2.51 | Dashboard | Dashboard | Created by team/sub-dept and top 5 issue filter in dashbaord
P-2.52 | Dashboard | Dashboard | DASHBOARD structure (add assigned tickets ) | Requirement | High
P-2.53 | Dashboard | Top performance | Top 5 ticket performers are showing from different company, Top 5 performer generation logic ? | Bug | High
P-2.54 | Dashboard | Dashboard reporting | "Created by Team" field option/column required in dashboard and report
P-2.55 | All features | Count | Show number behind features name after increasing or decreasing tickets, message or mail | Requirement | Medium
P-2.56 | All features | text body | While sending mail or message or creating ticket, if any error found for typing mistake or anything, it should show by underline | Improvement | High
P-2.57 | All features | Attachment | videos should be able to add while ticket creation, comments and messages | Requirement | High
P-2.58 | All features | IMAGE | Need to increase default image size after adding an image anywhere in the system so that previewing the image is not a must requirement to view the full image |  |  | https://prnt.sc/Py75uRO5Q64T https://prnt.sc/xYuZwEmSv7LL
P-2.59 | Notification | Ticket details | Enter into ticket details after clicking on Notification. Again, notification should not be vanished after clicking on a notification | Improvement | High
P-2.60 | System | Version | Mobile version in DigiGO | Requirement | High
P-2.61 | Reporting | Report | Created by, re-opened, resolved by, closed by columns need to show department, and user both in report
P-2.62 | Reporting | Report | Ticket Report download needs to be enabled | Requirement | High
P-2.63 | Reporting | Report download | Need single time download option, now it's requiring two time download to download the report
P-2.64 | Reporting | Report access | Need ticket generation access status filtering by "All, enabled, disabled" |  |  | https://prnt.sc/enpYz4pXSHns
P-2.65 | Ticket management | Ticket forwarding | After ticket forwarding, status is still showing "opened", it should show in-progress | Bug
P-2.66 | Ticket management | Ticket forwarding | While forwarding ticket, only 10 person is showing while searching user | Bug
P-2.67 | Ticket management | Priority | Assignee must not have the priority shifting option in three dot | Bug
P-2.68 | Ticket management | Company profile | In company profile template and category is showing wrong filter, data | Bug
P-2.69 | Communication | Mail | email should also be searched from replied mail | Bug
P-2.70 | Ticket management | Ticket creation | Alphabetical shortcode search not working for category/sub-category and product | 1st phase due |  | https://prnt.sc/jyO3VT_Vsc13
P-2.71 | sBusiness Portal | User management | NEED single user - multiple company assigning option | Requirement | Critical

## Feedback ¦ 31st July (hidden)
Sl | Module | Sub-module | Issue Title | Type | Attachment | Priority | Date | Status | SOC Review | User visiblity | Super admin visiblity
1 | Ticket Management | Create Ticket | While keeping and department in CC in ticket creation, CC shoud be visualize and it's optional , that should also be mentioned in bracket | Feedback | https://prnt.sc/Kh612pybBHBn | High | 2025-08-03 |  | Done
2 | Ticket Management | Create Ticket | Only priority should be shown in work flow based ticket but in SLA based , severity and priority both should be shown | Feedback | https://prnt.sc/9OoZ49fmMU0l https://prnt.sc/v4Nf-XuQgR2M | High | 2025-08-03 |  | Done
3 | Ticket Management | Create Ticket | All fields should be in row by row | Feedback | https://prnt.sc/HuN02kzpFD3_ | High | 2025-08-03 |  | Done
4 | Ticket Management | Create Ticket | Dropbox's element should be in dropbox style not as multiple choice type | Feedback | https://prnt.sc/SuwmIlnNZU83 | High | 2025-08-03 |  | Done
5 | Ticket Management | Create Template | Template Key will be set manually, which can from 2 letters to any but duplicate isn't allowed. | Bug | https://prnt.sc/PBN1rCs5X2iR | High | 2025-08-03 |  | Done
6 | Employee Management |  | Employee management will be aligned in central portal | Feedback | https://prnt.sc/en5JY1vlmaLD | High | 2nd Phase
7 | Dashboard |  | Ticket report as per requirement | Improvement | https://prnt.sc/aswSj5-yNEw0 | High | 2nd Phase
8 | Ticket Management |  | In SLA based ticket, anyone from the department should be able to forward the ticket | Feedback | https://prnt.sc/kzPa7Trug5b9 | High | 2025-08-03 |  | Done
9 | Ticket Management |  | Ticket status needs to be changed from "active, complete, canceled" to "opened, in progress, resolved, closed, re-opened, canceled" . | Feedback | https://prnt.sc/nNUXih2YGe6o https://prnt.sc/Vi5WmhdaR4ZZ | High | 2025-08-03 |  | https://prnt.sc/OyYUYZua_cIf https://prnt.sc/cZoNgKcXi6K6
10 | Ticket Management | Create Ticket | When a ticket is raised but no one starts working on it and it is not sent to the checker, it will remain as an “Open” ticket. Once someone checks it or starts working on it, the status will change to “In Progress.” | Improvement |  | High | 2nd Phase

## Dashboard and Reporting
Bug ID | Module | Sub-module | Issue Title | Type | Priority | Attachment | Status | SOC Review | UBD Review
B_ID_1 | Dashboard | 4 main cards | Unable to click on the main cards to show card wise status count. For admin other 4 cards are not also clickable. Need to show correct status count | Bug | Critical
B_ID_2 | Dashboard | Total tickets | "Total tickets" count needs to be generated by addition from the 4 cards ticket count, not all the tickets from organization. this ticket counts will not be changed according to card selection | Bug | Critical
B_ID_3 | Dashboard | Assigned tickets | "Tickets assigned to my dept" is showing same data of "assign to me"(ticket count) | Bug | Critical
B_ID_4 | Dashboard | Status | "Cancelled tickets" needs to raname as "Canceled tickets" | Bug | High
B_ID_5 | Dashboard | Filter | While filtering by department, template and product, it's showing wrong data | Bug | Critical
B_ID_6 | Dashboard | Filter | Priority filtering is not functional | Bug | Critical
B_ID_7 | Dashboard | Filter | Besides filter button, there was suppossed to be a "cross" icon to remove the filter, also need to show count how many filters are added. 1/2/3 | Improvement | High
B_ID_8 | Dashboard | Top 5 performers | Top 5 performers are not generating from specific filtering(dept,...) | Bug | Critical
B_ID_9 | Dashboard | Tickets of my dept | Tickets of my department is showing only the counts of "created by user's department" tickets. also Needs to show all ticket counts of assigned to user's department. | Bug | Critical
B_ID_10 | Dashboard | Filter | If the filter is not selected, all tickets of the 4 cards should be shown in the downloaded report , it's showing all tickets of the organization in the report | Bug | Critical
B_ID_11 | Report | Current department | After resolving the ticket, it still shows the "current dept" resolver's dept, After closing the ticket, it still shows the "current dept" resolver's dept. | Bug | Critical
B_ID_12 | Report | Third response time | Third response time is showing no time | Bug | Critical
B_ID_13 | Report | Resolution time | Resolution time is not showing any data(duration) | Bug | Critical
B_ID_14 | Report | Validation time loss | Validation time loss is not showing any data(time between resolve and close). for workflow based tickets: time between execution and closed. | Bug | Critical
B_ID_15 | Report | Employee interaction | In workflow based ticket, employee interaction is showing all from the workflow despite not taking any action by some of them | Bug | Critical

## Final feedbacks(phase-1)
Date | Sl no. | Module | Sub-module | Issue Title | Type | Attachment | Priority | Status | SOC Review | User visiblity | Super admin visiblity
30.07.25 | 1 | Ticket Management | Notification | Notification "check pending" or "approval pending" is not sending to 2nd checker or approver | It's working
| 2 |  |  | Severity and priority sequence needs to be exchanged. Severity<>priority | 2nd Phase
| 3 |  | All tickets | After creating ticket, the assignee person can not see his 'involvement type' in "All tickets", it's showing "not involved",, | It's working
| 4 |  |  | Ticket name column needs to be changed to "Ticket title" | It's working
| 5 |  |  | Ticket status should be "opened, work in progress, canceled, closed, re-opened",not 'active' and 'complete' | It's working
| 6 |  |  | Notification is not clickable, need to view ticket details after clicking on notification | Improvement
| 7 |  |  | Severity filtering is missing in "assign to me" | It's working
| 8 |  |  | Severity and priority should be fixed during creating ticket, not template | It's working
| 9 |  |  | In Ticket/template ID, short key field should be depatment name attached with ID, not ticket/template's first letters | It's working
| 10 |  |  | After creating a ticket, when user click on cross button instead of view ticket, it doesn't change the interface and create template "continue" option is still showing | It's working
| 11 |  |  | In notification, replace "ticked-ID" with "ticket title" | Improvement
| 12 |  |  | In SLA Based ticket, first checker needs to be "L1" , "checker". In "assign to me", my role will be "L1" | It's working
| 13 |  |  | While setting multiple option from dropdown, checkbox, after selecting , the data goes missing in that interface | Improvement
| 14 |  |  | "cross" button is not same in every section | It's working
| 15 |  |  | In all tickets, assignee person can not forward ticket, forward button is not clickable. but from "assign to me", assignee person can forward ticket | It's working
| 16 |  |  | "SLA breached" status is not showing instantly in the ticket details after SLA is over | It's working
| 17 |  |  | Templates needs to be "Department" specific and while selecting a template, "Search" option is required | It's working
| 18 |  |  | In SLA Based ticket, every (L1) from the department should be able to resolve and forward the ticket | It's working
| 19 |  |  | Template name is not visible in ticket details | It's working
| 20 |  |  | Ticket reporting function is missing | It's working
| 21 |  |  | SLA status and working status should be seperated | It's working
| 22 |  |  | After approve and execute, it should show approved and executed in that page just like "checked" | It's working
| 23 |  |  | in ticket details, showing wrong message | It's working
| 24 |  |  | Description dropdown is not required in template creation | It's working
| 25 |  |  | In SLA based tickets, user from the whole department should resolve, forward, close , cancel and re-open tickets, | It's working
| 26 |  |  | Tag should be typable while ticket creation | New Requirement
| 27 |  |  | After closing ticket, in ticket details, the status should be closed. | It's working

## Dashboard-Reporting (hidden)
Bug ID | Module | Issue Title | Type | Priority | Attachment | Date | Status | SOC Review
B_ID_1 | 4 main cards | It is not showing any colors, supposed to be 4 different colors as discussed . | Bug | High
B_ID_2 | 4 main cards | Any of the 4 cards or status is not clickable. According to the requirement. Need to show the status count after clicking on specific card and need to redirect to the ticket list after clicking on the status. | Bug | Critical
B_ID_3 | 4 main cards | 4 cards are visible in Admin dashboard, the section is named as "my tickets". need to rename it as "Tickets of my department" | Bug | Critical
B_ID_4 | Filter | While filtering department, it only shows the tickets created by that "department" , but need to show all the tickets related to the department(all 4 main cards) | Bug | High
B_ID_5 | Tickets of my dept | In 'tickets of my department section' , it only shows the tickets created by that "department" , but need to show all the tickets related to the department(all 4 main cards) | Bug | Critical
B_ID_6 | Create ticket | Previously "create ticket" option was at the top right side of the interface, after updating the dashboard it is missing, need ticket creating option from the dashboard as it was already in the system | Improvement | High | https://prnt.sc/_pk90-BKHYaP | next
B_ID_6 | Total tickets | "Total tickets" need to show total tickets count from all 4 cards For admin, it will remain same; but in organization tickets all tickets count will show | Bug | High | https://prnt.sc/xkU_-0D1r0Z3
B_ID_7 | 4 main cards | Tickets created by me and my department tickets need to be as 1st and 2nd card, Assign to me and assign to my dept tickets need to be as 3rd and 4th card. | Improvement | High | https://prnt.sc/lk90-Ay8jb8J
B_ID_8 | 4 main cards | For Admin, Card needs to rename from "waiting for approval" to 'Within SLA" . Also 2nd and 3rd card needs to be replaced | Improvement | High | https://prnt.sc/CBKmirwteh50
B_ID_9 | Filter | Filter will show count according to the numbers of filtering (1,2,3) and cross button to remove the filtering | Requirement | High | https://prnt.sc/4zRFPrjtV4Zj
B_ID_10 | Report | Escalation flow is not showing in the report | Bug | High
B_ID_11 | Report | First response time is showing time, need to show duration how much it took for first response | Bug | Critical
B_ID_12 | Report | Resolution time should show how much time it took to resolve the ticket(duration) | Bug | Critical
B_ID_13 | Report | Validation time loss needs to show how much extra time it took to solve the issue according to expected resolution time, it's not showing | Bug | High

## Bug(after test migration) (hidden)
Sl | Module | Sub-module | Issue Title | Type | Attachment | Priority | Date | Status | SOC Review | Dev Status | Remarks
|  |  | After test data migration, categories are showing while creating template, which should not be redirected here |  |  |  |  | pending
|  |  | In workflow based tickets, role is showing as L1 if there is only one checker for the ticket, but it should be checker/approver/executor |  |  |  |  | pending |  | Fixed
|  |  | Department, Sub-department is not showing in user profile |  |  |  |  | pending |  | Fixed
|  |  | Activity log is not showing according to the accurate flow. For this, the alignment is not clear to all the assignees |  |  |  |  | done
|  |  | After adding someone for CC in a ticket, all the other roles or involvement gone missing. If the ticket is in user's department and assignee's department he should be able to take action on the ticket. but currently he is not able to do that. (L2-CC) |  |  |  |  | Pending |  |  | Phase 2
|  |  | Sub-department can not be created for all the departments |  |  |  |  | done
|  |  | Dropdown filed is showing as Multiple choice field |  |  |  |  | done
|  |  | Unable to send document in mail |  |  |  |  | done
|  |  | Unable to send picture in message |  |  |  |  | done
|  |  | While creating a group in message, error message is showing despite the group being created |  |  |  |  | done
|  |  | While editing user information from Pulse, after clicking on edit button it is redirecting to a blank page |  |  |  |  | pending |  |  | Edit user from Portal
|  |  | In "assign to me", only priority column and filtering is showing |  |  |  |  | pending |  | Fixed

## Sheet11 (hidden)
Sl | Module | Sub-module | Issue Title | Type | Attachment | Priority | Status | SOC Review |  | Dev Status | Remarks
|  |  | Add category is not functional while creating ticket(unable to add new category) | [6 empty] | Done | Already in dev server
|  |  | Edit template button is missing | [6 empty] | Done | Already in dev server
|  |  | Unable to edit ticket | [6 empty] | Done | Already in dev server
|  |  | Inside the ticket, Ticket link is not valid | [6 empty] | Done | Already in dev server
|  |  | After forwarded by "Akash" to "Abir", it is showing "will check by Abir, but current assignee "Akash", should show current assignee "abir" | [6 empty] | Done | The requirement was like this.
|  |  | Unable to create new chat | [5 empty] | https://prnt.sc/eeTTu3llyWgb | Done | Already in dev server
|  |  | while creating a group all the users from the department is not showing for selection |  | https://prnt.sc/R2_Zv1Pq7C1K https://prnt.sc/ugcFd51MgGGD |  |  |  |  | Done | Already in dev server
|  |  | While selecting an assignee, user dropdown list doesn't show all the users from the selected department, it is showing only 10 users | [6 empty] | Done | Already in dev server
|  |  | After sending a message, it goes disappeared, conversation box remains blank (in dev, after scrolling down the message appears) | [6 empty] | Done | Give me some time to solve this bug.
|  |  | After resolving the ticket by someone from assignee's department, it still shows "will check by assignee" and sla still continues for assignee if he doesn't resolve it from his account. | [7 empty] | It was not in the requirement.

## 1st SEP (hidden)
1. Pulse ey dhukle communication, ticket management kono feature show korey na. er age multiple times ei issue solve hoise, abar arise hoise. (Hadi vai ke call ey paini. slack, whats app groupey dea hoise). kalke issue fixation er deployment arrange kora jayni kubernetes- unusual issue er jonno. Hadi vai kaj kortese eta niye
2. SBE team er karo account creation complete hoyni. single user multiple company te add thakte parey na. (Sohag vai ke abar inform kora hoise. uni boltese eta korte time lagbey)
3. CX team er major kisu point jegulor jonno Pulse onboarding ey problem.
* Reporting - Ticket report download
* Dynamic SLA according to category,sub-category
* while category, sub-category selection need search option.
* Ticket closing should not be restricted to the ticket creator's department because confirmation of the issue fixation by call centre is time consuming.
* If the ticket is not visible to all the users, there is a risk of duplicate ticket creation
4. KYC team agreed to create ticket in Pulse for shebaPay related issues, but no response till now.
5. IT related issue er jonno ekhono gPlex ey ticket kora hocchey.
Chat feature is not functional
Unable to take screenshot from mail
All mails feature should be added . should be able to search by any word from inbox/ sent/draft
After forwarded by "Akash" to "Abir", it is showing "will check by Abir, but current assignee "Akash", It should show current assignee "abir"
After closing the ticket by someone from assignee's department, it doesn't show in activity log "closed by..........". it still shows "will check by assignee" after resolving the ticket.
Pic size should be increased in ticket details
after clicking on continue, need error msg if any field is missing
error underline if there is a wrong spell

## Discussion feedbacks (hidden)
Sl | Module | Issue Title | Description | Attachment | Type | Priority | Date | Status | SOC Review | User visiblity | Super admin visiblity
1 | Ticket Management | "Open" Template type should be renamed as "Escalation based". Escalation level: Level 1, 2, 3. |  |  |  |  | 22.07.25
2 |  | "Fixed" template type needs to be renamed as "Workflow based"
3 |  | Severity and priority should be fixed while creating ticket, not while creating the template. SLA time will not be fixed, SLA type needs to be fixed in ticket (severity , priority) e.g:S1P1
4 |  | Ticket management will have 4 features: My department, My tickets, Assigned to me, CC tickets
5 |  | In my department, all the templates of my department will be stored, will be able to create ticket from here and tickets raised in my department will be visible
6 |  | While creating tickets, Ticket id needs to be incremental automatically
7 |  | In Details section, Current "Assignee" or checker will be seen
8 |  | "Approval hub" needs to be renamed as "Assigned to me"
9 |  | Ticket id will be in URL after entering into that ticket
10 |  | Priority type: Critical(p1), major(p2) , moderate(p3), minor(p4) Severity type: S1, S2, S3, S4
11 |  | Ticket title should be editable
12 |  | While creating a ticket, there will be a dropdown option for setting severity, priority. (e.g: s1p1, s1p2, s2p4)